## 784-BNEEN282781 CLID-VR-RevB
Comments Log for: |  | (CLID) Validation Report - Newdegate Street, Greenslopes Queensland
Comment ID: | Reviewers: |  |  | Document: | Validation Report, Newdegate Street, Greenslopes Queensland (Report ref. 784-BNEEN282781 Validation Report, dated 22/02/2024)
1 onwards | Reviewer - Louise Cartwright (Epic) |  |  | Site: | 114 Newdegate Street, Greenslopes (Lot 123-125 RP46047)
100 onwards |  |  |  | Revision number: | Rev B
1000 onwards |  |  |  | Document received: | 2024-02-23
|  |  |  | Review comments returned: | 2024-02-29
Comment No. | Reviewer | Doc Rev | Review date | Reference/ Report Section | Review #1 Comment [29/2/2024] Comment on Rev B | Review #1 SQP Response [Date] | Review #2 Comment [Date] | Review #2 SQP Response [Date] | Date Action Closed | Comment Status (Open / Closed)
1 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | Epic have been commissioned by Dave Binny of Department of Verteran's Affairs (the Client) to provide contaminated land auditor (CLA) services for the removal of the site (Lot 123, 124 and 125 on Registered Plan (RP)46047) from the Environmental Management Register (EMR). It should be noted that the CLA services for this site were undertaken in general accordance with the provisions of the (Qld) Environmental Protection Act 1994 (EP Act). | Comment noted |  |  |  | Open
2 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | The comments and advice are provided to assist the Suitably Qualified Person (SQP) to progress finalisation of the CLID. The information should not be considered pre-emptive of the final report submission for the site, but rather represents the reviewers' opinions based on the current review of available site information. The comments are not designed to be an endorsement or certification of meeting the requirements of the EP Act, but rather are considered as comment only. | Comment noted |  |  |  | Open
3 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | It is understood that the Validation Report (VR) forms the Contaminated Land Investigation Document (CLID) report. Thus, this CLID-VR must be accompanied with a completed DES submission form. Recent regulatory changes, require as of 5 April 2023, the new CLID form https://www.qld.gov.au/__data/assets/pdf_file/0031/375448/cl-investigation-document-form.pdf to be submitted with the CLID. Parts A to C and Appendix 1 and Appendix 2 of the form must be completed by the SQP, whilst the Auditor completes Part D. A completed copy of the CLID form by the SQP was not provided with this draft CLID-VR to the CLA. Thus, the information provided to date is not considered to be in a 'CLID approved form'. Furthermore, the CLA is unable to comment on whether the CLID submission form has been appropriately filled out. | A copy of the completed Contaminated Land Investigation Document form (Version 1.03) has been submitted with Rev C of the CLID. |  |  |  | Open
4 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | The CLA understands the Client's intension is to remove the site from the EMR. Thus, the SQP is not required to develop a Site Management Plan (SMP) as part of the future CLID. | Comment noted |  |  |  | Open
5 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | It is generally the CLAs preference that CLIDs are prepared as standalone documents with all pertinent information provided in the main report text, thereby negating the requirement for significant documentation to be appended. | Please refer the response to Comment 9. |  |  |  | Open
6 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | It is recommend that Coffey include a table in Section 1 which details key project information including details of the SQP (and support team, if applicable), the CLA, Client, EMR status / IDs and CLID type / trigger. Sample text to consider for inclusion (to populate CLID type / trigger section) : "Voluntary submission of a CLID comprising an assessment of potential site contamination – Removing Site from the EMR. This CLID provides final information about the Site and its intended use. No more CLIDs are forecast in the foreseeable future for the same Site and its same intended use" | Please refer to Table 1-1 in Section 1. |  |  |  | Open
7 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | Mapping needs to be provided for all desktop searches including but not limited to topography (including contours), watercourses / drainage, hydrogeology (location of bores within a 2km radius of the site), regional and local geology, soils, acid sulfate soils, flood risk assessment, bushfire, fire ant, unexploded ordnance and cultural heritage. Please ensure all these searches are discussed in the final CLID | Please refer to the amendments to Section 4.4 which includes references to the requested figures which are provided in Appendix K. |  |  |  | Open
8 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | The report indicates that the site is located at 114 Newdegate Street, Greenslopes QLD, however, the addresses relevant to the site are 51, 53 and 55 Headfort Street. Recommend that either Coffey remove reference to Newdegate Street or that clarity is provided | The site has been historically referred to as 114 Newegate Street, Greenslopes (common address). The address will be changed to 51, 53, 55 Headfort St and footnote is to be added to the CLID explaining that 114 Newdegate Street has also been used historically to describe the address of the site. |  |  |  | Open
9 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 3.1 Site Characterisation | Provide details of previous investigations in this section including scope of works, key findings, and provide comment on any limitations and compliance with relevant guidelines and standards relevant to this CLID | Section 3 has been renamed 'Previous Investigations'. Details of previous investigations have been summarised in this section. The summary of contamination has now been included in Section 4.5 |  |  |  | Open
10 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.1 Site Identification | Add "Current Occupiers" to Table 4-1 and list as "none" - assuming this is accurate | Please refer to ammendment to Table 4-1. |  |  |  | Open
11 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.1 Site Identification | Table 4-1: The site address is listed as "53 Headfort Street" for all three lots. Please update to reflect actual addresses - i.e., 51, 53 and 55 Headfort Street | Refer to response to comment 8 |  |  |  | Open
12 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.1 Site Identification | Table 4-1: EMR Listing - please update text to reflect description in the register "The site has been subject to contamination from a hazardous contaminant as follows: HAZARDOUS CONTAMINANT - This site has been subject to a hazardous contaminant. Elevated concentrations of organochlorine pesticides (DDD/DDT/DDE and Aldrin/Dieldrin) identified on site above the nominated investigation levels." Provide a short history (if available) of when any listing(s) occurred, and any changes that were made to the listings. | Refer to amendments to Table 4-1 and Appendix K.2 |  |  |  | Open
13 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.1 Site Identification | Table 4-1: The surrounding land uses have not been captured on figures. Please include | Please refer to amendments to Table 4-1 and the figure included in Appendix K.13 |  |  |  | Open
14 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.1 Site Identification | Table 4-1: The utility services (pre and post remediation) need to be captured on a figure and further consideration. Did underground services have the potential to act as a conduit for contamination? | Section 4.2.8 has been prepared to describe utilities pre/post remediation. Pre-remediation utilities removed during remediation are to be provided by EPS. Section 4.2.8.1 will be updated with this information once it has been provided. Figure 12, Appendix A which shows the location of underground utilities post-remediation. Thee are described in Section 4.2.8.2 and 6.6.2 The following statement has been included in Section 4.2.8.3: The contaminants of concern for the Site (refer to Section 3.5 and Section 4.2.10) are non-leachable (asbestos) or have low solubility/leachability (OCPs) and therefore the migration of contamination along preferential pathways which may be associated with building services (e.g. bedding sands) is not an applicable transport pathway for the migration of contamination on the Site. |  |  |  | Open
15 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.1 Site Identification | Ensure to describe all surface and subsurface infrastructure on the land, including details of the location, size and type of the infrastructure. Relevant infrastructure includes pipes, tanks, drains, dams, bores, buildings and foundations. Further details relating to the site buildings would be beneficial (e.g. any material changes to building since construction? when did it fall into disuse? was it accessible to the public? potential for lead paint occurrence considered?) | Please refer to the information included in the following sections: 4.2.2, 4.2.4, 4.2.7 which describes the structures and infrastructure historically present on the Site. Information on lead based paint is provided in Section 4.2.7. Infrastructure/activities not undertaken on the Site are described in Section 4.2.9. |  |  |  | Open
16 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.2 Site History | Historical Aerials have not been provided to the CLA for review. Please provide noting that the imagery provided in the report is not of sufficient resolution for review purposes. Please also provide in the final CLID noting it would be useful to include the site boundary on the historical aerials | Please refer to the amendments to Section 4.2 and the historical aerial imagery included in the Lot Search Report provided in Appendix K.1. |  |  |  | Open
17 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.2 Site History | The information provided in this section is not sufficient to ensure the site history and associated contaminants of potential concern are fully understood. It is recommended that information from previous investigations is incorporated into this section and reference from where this information has been sourced is also included | Please refer to: Section 3 which summarises data from Previous Investigations. The Summary of Contamination previously included in Section 5 has now been moved to Section 4.5. Section 4.2 which includes further information on the history of the Site from previous investigations (refer to Section 3) and the Lot Search Report included in Appendix K.1. Contamination on the Site as it relates to historical landuse has been summarised in Section 4.2.10. As requested the CSM previously included in Section 6 has now been moved to Section 4 (now as Section 4.6). |  |  |  | Open
18 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.2 Site History | Confirm purpose of the following statement "It is not known whether historically there were smaller structures located on the Site which have subsequently been demolished and the source of any fill material used on the Site." Is there a reason why this comment has been included? What lead Coffey to believe this may be the case and how has this potential been considered during site remediation? | The statement "It is not known whether historically there were smaller structures located on the Site which have subsequently been demolished and the source of any fill material used on the Site" has been removed from the CLID is Section 4.2. |  |  |  | Open
19 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.2 Site History | Has a Right to Information (RTI) application been submitted to the Department of Environment Science and Innovation (DESI) and local council? Please provide these records and also include in the CLID-VR | Please refer to Section 4.2.5 and Section 4.2.6, and the records included in Appendix K.2 and K.3 |  |  |  | Open
20 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.2 Site History | What about data gaps? Noting some are indicated in the SAQP | Discussion on data gaps following completion of investigations is discussed in Section 3.1.4, 3.2.4, 3.3.4 and 3.4.4. The data gaps referred to in the SAQP are reproduced in Section 3.4.1. The data gaps referred to in the SAQP related to aspects of the site which has not been previously investigated rather than data gaps relating to the history of the site. Please refer to Section 4.2.11 in regard to data gaps associated with site history. |  |  |  | Open
21 |  |  | 2024-02-29 | 4.2 Site History | Please provide statement whether waste has / has not been disposed or stored on land (refer to module 6 for more guidance, if required) | Please refer to Section 4.2.9. |  |  |  | Open
22 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | Comment on present (or absence) of ERAs or enforcement notices relevant to the site / surrounding land. Refer to module 6 for more guidance | Please refer to Section 4.3.2 |  |  |  | Open
23 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.3 Environmental Management Register | First time DDD/DDT/DDE have been used - provide acronyms in full | These acronyms have now been defined in Section 1 Introduction and the ACRONYMS/ABBREVIATIONS table. |  |  |  | Open
24 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | More detail is required in this section - a summary of previous investigations does not provide sufficient information for CLID requirements. As previously stated, mapping should be provided for CLA review but should also be attached to the CLID-VR and referenced throughout this section. It is noted that some of this information is captured in supporting documentation (e.g., SAQP) but needs to be added to the CLID-VR which should be a stand alone document | Please refer to the amendments to Section 4.4 |  |  |  | Open
25 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | The report indicates that topography flows toward Norman Creek. It is noted that Glindemann Creek is also located south of the Site and should be discussed. Topography is discussed in "regional geology" - consider adding this to the "topography & drainage" item instead | Please refer to Section 4.4.2 |  |  |  | Open
26 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | First time Ekibin Park East mentioned - add to surrounding land uses and indicate on Figure | Please refer to the amendmetns to Section 4.4.1. The location of Ekin Park East is shown in Appendix K.6. |  |  |  | Open
27 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | Where is the BCC stormwater drainage system relative to the site? Add to figure | Please refer to the amendments to Section 4.4.2 and the map included Appendix K.15 |  |  |  | Open
28 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | The registered bore search should be extended to 2km as only one bore is located within a 1km radius of this site. Please add to figure and also depict this radius | Please refer to amendments to Section 4.4.7. Regional bore information within a 2 km radius of the Site is included Appendix K.1. |  |  |  | Open
29 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | m bgs - first time used (in full) | m bgs is now first used in Section 3.2.3, and is defined in the ACRONYMS/ABBREVIATIONS |  |  |  | Open
30 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | Regional geology of the surrounding land should also be discussed | Refer to the amendments to Section 4.4.3. |  |  |  | Open
31 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | Local Geology - reference which previous site investigation these subsurface geology described were derived. Comment on heterogeneity (or otherwise) of the fill and natural soil profile observed during previous investigations and remediation. Also noting topsoil was identified during the remediation phase of the project. Recommend that Coffey include a table in an appendix which details the sample event, lithology, anthropogenic waste encountered and the total depth of each location - I note that some of this information is captured in Figure 3 | Please refer to Section 4.4.4 and the previous investigation lithological table included in Appendix K.4. |  |  |  | Open
32 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.4 Environmental Setting | It is noted that mudstone was encountered between 0.65 and 2.4 m bgs in the north western portion of the site. Was bedrock encountered elsewhere on site? If not, please provide further information including the anticipated geology / depth it would likely be encountered | Please refer to Section 4.4.4. Weathered mudstone was encountered from 2.9 m bgs. Weathered rock was not encountered eleshwere during previous investigations due to the depth of investigation locations being <0.5 m bgs. |  |  |  | Open
33 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.5 Regional Ecosystems | Please provide this mapping and include in final CLID. A link is not sufficient. | Please refer to Section 4.4.13 and Appendix K.16 |  |  |  | Open
34 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 4.6 Environmental Values and Water Quality Objectives | Please provide the associated map and Environmental Values and Water Quality Objectives report. These should also be included in an appendix and referenced accordingly | Please refer to Section 4.4.15 and Appendix K.17 and K.18 |  |  |  | Open
35 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | Include a section on groundwater dependent ecosystems | Please refer to Section 4.4.15 and Appendix K.1. |  |  |  | Open
36 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | Noting that areas of potential environmental concern (APECS) and potential contaminants of concern (CoPCs) have not yet been discussed | Refer to Section 4.5.5 and Section 4.5.6 |  |  |  | Open
37 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | Key information from the SAQP and RAP should be captured in the report (DQOs, Investigation criteria applied and why etc.). Were works conducted in accordance with these documents? | As requested the DQOs and Investigation Criteria included in the SAQP have been reproduced in Section 3.4.2 and Section 3.4.4 respectively. Section 3.4.5 has been added to note that the Investigation Levels were further refined in the Supplementary Investigation, and that the Investigations Levels included in the report on the Supplementary Investigation have been reproduced in 3.4.5. Section 3.4.1 and 3.4.8 includes a statement that the Supplementary Investigation was undertaken in accordance with the SAQP. The DQOs include references to other Sections of the SAQP document. The SAQP has therefore been included as an appendices to the report (see Appendix L.1). DQOs form the RAP have been reproduced in Section 5.3. The DQOs include references to other Sections of the RAP document. The RAP has therefore been included as an appendices to the report (see Appendix L.3). Remediation critieria from the RAP are described in Section 5.4. A statement of work being completed in accordance with the RAP is included at the end of Section 6.2. Statements about the remediation works being undertaken in accordance with the RAP were previously included in Rev B in Section 8.3 (now 6.3), 8.4.1 (now 6.4.1), 8.4.2 (now 6.4.2), 8.5 (now 6.5), 8.9.1 (now 6.9.1), 8.9.4 (now 6.9.4), 8.10 (now 6.10). |  |  |  | Open
38 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | More detailed information relating to site / soil conditions and the time period these investigations took place would be beneficial. Any limitations or data gaps identified? Analytical tables should be provided in Appendix C (in addition to the remediation analytical data) which clearly indicate the historic samples that have been removed from site during remediation and those remaining onsite | The summary of contamination is now included as Section 4.5. Please refer to the amendments to this Section and note: * previous site investigation data tables included the RAP are not provided in Appendix C.7.1 and C.7.2 * a statement in regard to the removal of the materials which include the sample data is included in Section 4.5.8 * data gaps / limitations are described in Section 4.5.7. * reference to absestos being found in remediation and managed as an unexpected find is included in Section 4.5.8. |  |  |  | Open
39 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | Note on chromium: detail whether chromium VI was considered a CoPC. Have these locations (or subsequent locations) been speciated to confirm that chromium concentrations are CrIII other than at MW1? Noting that elevated Cr concentrations appear to be primarily along the eastern boundary of the site. Note, the concentrations of Cr at MW1 are currently unclear. | Please refer to the amendments to Section 4.5.2.4 |  |  |  | Open
40 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | BH16 is missing from Figure 2. | BH16 is in the south eastern corner of the Site, and was shown in Figure 2 and Figure 3 in Appendix A. |  |  |  | Open
41 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | Should "A04" be "SA04/A04" and "A06" be "SA06/A06" | Refer to amendments to Section 4.5.2.2. A04 has been changed to SA04/A04, A06 has been changed to SA06/A06 and A10 has been changed to SA10/A10. |  |  |  | Open
42 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | Where is A10? Where under the main hall, accommodation building and unsealed external areas was asbestos encountered - clarity on how widespread asbestos was encountered would be beneficial. Any changes should also be captured on the relevant figures | SA10/A10 is in the north eastern corner of the main hall building. Additional information has been added to Section 4.5.2.2 on the inferred distriubtion of asbestos. Amendments to the figures is not considered to be required. |  |  |  | Open
43 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | What is the 2021 investigation? This is not mentioned in Section 3.1 (also mentioned in Figures). | 2021 Investigation' changed to 'Supplementary Investigation' |  |  |  | Open
44 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | This section reads as items that should occur - recommend Coffey use past tense to indicate these were measures that were implemented in subsequent remediation / site management | The section has been changed so it is in the past tense. Additional sentences have been added to Section 4.5.2.1, 4.5.2.2, 4.5.2.7 and 4.5.8 to note that the materials requiring remediation (including fill) have been removed from the Site as part of the remediation works undertaken in 2023. |  |  |  | Open
45 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | Confirm concentrations of TRH observed at SS04 and confirm if silica gel clean up was conducted? CLA notes this location is located adjacent to the north eastern site boundary | Silica gel clean up was not undertaken, and was not considered to be required in 2013 based on the lines of evidence discussed in this section (now Section 4.5.2.6). As requested the following sentence has been added. "Notwithstanding the above the soil material represented by sample location SS04 was removed as part of the remediation works undertaken in 2023 (refer to Section 6)." |  |  |  | Open
46 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | "Fill containing anthropogenic materials which pose physical hazards (sharp and angular) have been observed on the site and are considered to be unsuitable for use in a park/open space and should also be removed from the Site where there is a likelihood that future users of the Site may come into contact with these materials". Please ensure this comment is closed out / confirm this management action was implemented | Reference to these materials has been included in the following: * Section 4.5.2.6 * text description in Pre-remediation CSM in Section 4.6, tabulated CSM in Section 4.6.1 and illustrative CSM in Figure 15, Appendix A * removal fo these materials in association with the removal of fill materials in Section 6.9.3.4 |  |  |  | Open
47 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | EILs - was site specific criteria applied? Please include calculations in an appendix | To respond to comment 37 the report on the Supplementary Investigation has been included as Appendix L.2. The derivation of investigation criteria including the EILs have been included in Section 3.4.5. |  |  |  | Open
48 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.0 Summary of Contamination | First time application of termiticides have been mentioned in the CLID-VR | The application of termite barrier / termiticides is as source of OCP contamination was described in Section 1, Section 3 and Section 4 of the previous version of the CLID. Section 1 has been amended to state "OCPs are associated with historical application of termite barriers using termiticides around buildings,". As similar sentence has been added to Section 4.5.2.1. The phrase "termite barriers" has been added to sentences using the word termiticides in the pre-remediation CSM included in Section 4.6. |  |  |  | Open
49 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.2 Groundwater | "A groundwater monitoring well was installed in the north western corner of the Site to 6 m bgs (refer to MW01 in Figure 2, Appendix A) in the Supplementary Investigation (refer to Appendix K). Groundwater was not intersected and is likely to be at a depth greater than 30 m bgs." How was the determination made that groundwater is >30 m bgs? I note that that the RAP states that "no groundwater was encountered in the monitoring well when it was gauged approximately one week later on the 24 November 2021". Were there any further attempts to gauge the well? A discrepancy of gauging event was previously identified by the CLA - has this been rectified? Have seasonal variations been considered? Some reference documents for Coffey consideration: https://eisdocs.dsdip.qld.gov.au/Completed%20Projects/Cross%20River%20Rail/EIS/EIS%2030%20Aug%202011/01%20Volume%201/12%20Groundwater.pdf https://eisdocs.dsdip.qld.gov.au/Completed%20Projects/Cross%20River%20Rail/EIS/EIS%2030%20Aug%202011/01%20Volume%201/07%20Soils%20Topography%20and%20Geomorphology.pdf https://eisdocs.dsdip.qld.gov.au/Completed%20Projects/Cross%20River%20Rail/EIS/EIS%2030%20Aug%202011/03%20Volume%203/Technical%20Report%204%20Groundwater.pdf | Please refer to the amendments to Section 4.4.7 which now includes reference to relevant information from the Cross River Rail EIS, how groundwater at 30 m bgs was estimated from bore information, and provides further information on why a shallow groundwater bearing zone is unlikely. The requirement for further gauging of MW1 was not identified in the report of the Supplementary Investigation, and accordingly was not undertaken. The report on the Supplementary Investigation concluded that the risk to groundwater from OCPs on the Site was low based on the solubility/leachability (mobility) of these contaminants, and the absence of a shallow groundwater bearing zone. Please refer to the additional response to comment 50. TTC is not aware of an discrepancies in gauging events previously identified by the CLA. There was a comment from the Site Auditor on the RAP that the CLID needed to: - Provide details on aquifer types (unconfined, semi-confined, confined) and aquitards/aquicludes present - Provide details on current usage and likely resource potential TTC intend that Section 4.4.7 has resolved these comments. |  |  |  | Open
50 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 5.2 Groundwater | The 2023 approved form requires the SQP to consider groundwater for example, “Confirm that the CLID addresses referenced sections of the NEPM Schedules B1, B2, B3 and B6…. For the CLID to be in the approved form, the sampling program must have collected sufficient data to establish the nature and vertical and lateral extent of contamination in all relevant media. Where mobility of a contaminant is an issue, properties such as contaminant leachability and groundwater and soil vapour flow direction must be assessed.” It is noted that Section 8.1, Schedule B2 of the NEPM discusses the groundwater investigation which is not detailed in the CLID. It is expected the SQP justify within the CLID the target depth of 6m for the single groundwater well, and the location in the NW corner of the site (which deviates from the proposed location proposed via email correspondence to the CLA). | The location/depth of MW01 in the north west corner of the Site was communicated to the Site Auditor on the 15/11/2021 in an email, and the Site Auditor responded to this email on the same day. This email was submitted as an addendum to the SAQP and for clarity the email/response has been included in Appendix L.1. Please refer to Section 3.4.3 which describes the rationale for the monitoring well in the north western corner, and the depth of the monitoring well. Groundwater on the Site is discussed further in Section 4.4.4 including a discussion on the likeihood of a shallow groundwater bearing zone. Risk to groundwater is discussed further in Section 4.5.3. The following text has been included in this section. "A groundwater monitoring well was installed in the north western corner of the Site to 6 m bgs (refer to MW01 in Figure 2, Appendix A) in the Supplementary Investigation (refer to Section 3.4). Groundwater was not intersected and is likely to be at a depth greater than 20 m bgs (refer to Section 4.4.7). Risk to groundwater receptors was considered to be low based on the following lines of evidence: • OCP contaminants on the site strongly absorb to soils and have low solubility/leachability. This is demonstrated by elevated concentrations of OCPs being reported in the upper soil materials (<0.2 m bgs) where the termiticides were historically applied, and substantially lower concentrations in deeper soil materials (>0.2 m bgs) which provides an additional line of evidence to support the conclusion the OCPs have low leachability/solubility on the Site. The risk of these contaminants leaching to underlying groundwater is therefore considered to be low. • No shallow water bearing zone has been identified within 6 m of the ground surface, and conditions on the Site and surrounding area are unlikely to result in the formation of shallow water bearing zone (refer to Section 4.4.7). The DES Contaminated land investigation document – approved form, Version 1.03, 19 May 2023 states the following on Page 6 of 24: For the CLID to be in the approved form, the sampling program must have collected sufficient data to establish the nature and vertical and lateral extent of contamination in all relevant media. Where mobility of a contaminant is an issue, properties such as contaminant leachability and groundwater and soil vapour flow direction must be assessed. As noted above the investigation data for the Site has established that elevated concentrations of OCPs are in the upper soil materials (<0.2 m bgs) where the termiticides were historically applied, and OCPs have low solubility/leachability and therefore low mobility and are held in solid (soil/fill) media. Accordingly, it can be concluded that mobility of the contaminants is not of concern and therefore further consideration into contaminant leachability and sampling of groundwater media (i.e. in the NFB) is not warranted. Post-remediation (refer to Section 6) risk to groundwater is considered to be negligible on the basis that the source of contamination requiring remediation has been removed from the Site." |  |  |  | Open
51 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 6.0 Pre-Remediation Conceptual Site Model | "Contamination present in soil and other environmental media as a result of the primary source is considered as a secondary source of contamination." What other environmental media? | Reference to other environmental media is to removed from the pre-remediation CSM which is now included in Section 4.6. |  |  |  | Open
52 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 6.0 Pre-Remediation Conceptual Site Model | Has leachability testing been completed? Please supply the results in Appendix C | TCLP leachability data has been included in Appendix C.7.2 and is referenced in Section 3.4.7 and the second paragraph of Section 4.5. |  |  |  | Open
53 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 6.0 Pre-Remediation Conceptual Site Model | It is expected that Source / Pathway / Receptor sections are included with written explanation, which are then summarised in the table. A CSM figure would be helpful | The pre-remediation CSM presented in Section 4.6 (formerly section 6) included a written explaination and then a table. A CSM figure has been included as Figure 15, Appendix A. |  |  |  | Open
54 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 6.0 Pre-Remediation Conceptual Site Model | The discussion of groundwater applicability must be presented in a 'pathways' section. | Additional information to been added to the pre-remediation CSM (now in Section 4.6) text description of the groundwater pathway. This draws information included in Section 4.4.7 and 4.5.3. |  |  |  | Open
55 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 6.0 Pre-Remediation Conceptual Site Model | Note 2 missing from the table. Typos in table | Note 2 has been added to the table. Typos have been amended (references to notes and the Property has been change to the Site. |  |  |  | Open
56 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 7.3 Remediation Criteria | Is it a coincidence that elevated arsenic is noted at locations directly adjacent to locations "SLAG1" and "SLAG2"? | The maximum concentration of arsenic reported in previous investigations is 32 mg/kg at SS01 which was located in the middle of the Main Hall Building, and not near Slag 1 or Slag 2 sample locations. All samples had concentrations of arsenic well below the NEPM HIL-A / EIL guidelines (100 mg/kg) and no samples reported elevated concentrations of arsenic which would indicate that arsenic was historically used as a termiticide. Slag 1 and Slag 2 samples reported non-detectable concentrations of arsenic. The nearest sample locations to Slag 1 (6 and HA02) reported a maxmimum arsenic conentration of 14 mg/kg. The nearest sample locations to Slag 2 (7 and HA03) reported a maxmimum arsenic conentration of 20 mg/kg. Additional information has been added to the CLID to confirm that arsenic is not a contaminant of concern associated with the use of termiticides on the Site. Refer to Section 4.5.2.5 and 4.2.10. |  |  |  | Open
57 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 7.3 Remediation Criteria | What does TTC mean? | Tetra Tech Coffey. Abbreviation is now included Section 1 and the ACRONYMS/ABBREVIATIONS table. |  |  |  | Open
58 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.2 Summary of Remedial Works | Ektimo should be identified in Section 8.1 | Ektimo has been added to Section 6.1 (former 8.1) in Table 6.1. |  |  |  | Open
59 |  |  |  | 8.3 Inspections During Remediation | Table - from 4/12/23 onwards does not reflect site works eg "During the inspection it was agreed that further excavation was to take place along the full extent of the western boundary (approximately 0.3 m in width and 0.1 m deep) and there was not a requirement to undertake further excavation in service trenches where asbestos had been reported". Further detail on additional remediation works is required. Further remediation works were on the northern not western boundary | Please refer to the amendments to 4/12/23 to clarify that the excavation took place along the northern boundary. |  |  |  | Open
60 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.7 Disposal of Excavated Materials | Were soils transported directly off-site or temporarily stockpiled on site? Details of soil movement and tracking have not been presented | Soil materials were not stockpiled and were loaded directly into skips for off-site disposal. The following sentence has been included in Section 6.5 "Excavated materials were not stockpiled on the Site and were placed directly into skip bins and covered. Photographs of covered skip bins are provided in Section 6.7." The following sentence was previously included in Section 6.7 (formerly 8.7). " Excavated materials were placed directly into skip bins and covered." and has been amended to state " Excavated materials were not stockpiled and were placed directly into skip bins and covered." Tracking records from EPS are to be included in Appendix H.2 (once updated tracking records are provided by EPS). |  |  |  | Open
61 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.7 Disposal of Excavated Materials | Ensure additional information by EPS (as noted to be provided in the final CLID-VR) is included. I would also like the details of the permit versus the actual disposal volume is more clearly articulated in the report as it is currently difficult to follow. It is noted that a bulking factor of 1.5 has been applied and that volumes exceed the waste levy exemption of 910 tonnes | EPS advised there was an administrative error; this is being correct with the BMI Group and DES. This section (now 6.7) will be updated once this information has been completed. |  |  |  | Open
62 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.8 Imported Materials | Paragraph under Table 8-6. Worth identifying that results were below the adopted investigation levels / remediation criteria - is there a difference in these criteria? Photos of this material would be beneficial | Validation results for imported materials were previously presented in Section 8.9.4, and are not included in Section 6.9.6. Please note that additonal validation data has now been included for Cr VI and is discussed in this Section. |  |  |  | Open
63 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.9.1 Overview | Table 8:7 - Please add suffix used in Sample IDs in the analytical tables (Appendix C) | The suffix described in the Table 6.7 (former Table 6.7) were included in the Sample IDs in the validation samples included in Appendix C.1.1, C.1.2. Columns were also included in Appendix C to include a description of the sample location (e.g. wall or floor) and the material sampled (e.g. Ash Fill, natual ground, etc.) which relate back to the suffix. |  |  |  | Open
64 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.9.2 Final Validation Sample Results | Lead - why was HSB04_F_231016 collected if it was not within a road reserve and not within site? | HSB04 was collected from the wall of the excavation as required in the RAP. The exacation boundary along the western side extended approximately 0.5 m beyond the site boundary into the BCC road reserved. HSB04 was therefore collected from the wall of the excavation in the BCC road reserve. The following paragraph was previously included in Section 8.9.2 (now Section 6.9.3.2). Lead Lead exceeded the remediation criteria in one sample (HSB04_F_231016) with a concentration of 370 mg/kg. This sample was collected from fill material west of the western boundary of the Site within the BCC road reserve (and therefore not within the boundary of the Site). The following sentence has been added to this paragraph. "The result from this sample is not considered to be a risk to future users of the Site noting the material sampled is 0.5 m west of the Site Boundary." |  |  |  | Open
65 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.9.2 Final Validation Sample Results | ASLP - first time used. The assessment of leachable analysis should be provided in this CLID-VR | The assessment of leachability of arsenic was discussed in Section 6.9.3 (formerly 8.9.2) and Appendix J (now J.1). Sufficient information is considered to have been provided to address the boundary exceedence in relation to arsenic. |  |  |  | Open
66 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.9.2 Final Validation Sample Results | Please provide all statistical analysis in an appendix | Statistical anlaysis in relation to arsenic was included in Appendix J (now appendix J.1). Appendix J is referred to correctly in Setion 7.3 (now Section 5.4) and incorrectly referenced in Section 8.9.2 (now Section 6.9.3). The reference to Appendix K has been changed to Appendix J.1. |  |  |  | Open
67 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.9.2 Final Validation Sample Results | Section 8.9.2.3 is unclear. The asbestos samples identified in the bullet points are understood to be either offsite (HS10) or were further excavated (T02, T04 and T05). Samples T02, T04 and T05 were discussed in a site meeting on 4/12/23 and further excavation agreed. It is noted an email was provided by Coffey stating TS02_B, TS04_W1 had exceedances for asbestos however, these locations were not presented on the figure 7 provided in the email and assumed to be T02 and T04, which were part of the northern boundary remediation. This further remediation is briefly mentioned in Section 8.3 to have occurred 13/14 December 2023. Please clarify. | Please refer to the amendments to 6.9.3.3 (formerly 8.9.2.3) and the supporting Appendix J.2. |  |  |  | Open
68 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.9.2 Final Validation Sample Results | "In summary based on the final validation results the remedial objectives and remediation criteria are considered to have been achieved, and the Site can be considered to be suitable for any use." Consider rephrasing for clarity | The sentence in 8.9.2 (now 6.9.3.5) has been amended as follows "In summary based on the final validation results, the remedial objectives and remediation criteria are considered to have been achieved, and the Site is considered to be suitable for unrestriced land use." |  |  |  | Open
69 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 8.10 Quality Assurance and Quality Control | This section needs to be further assessed to confirm reliability of field procedures and analytical results comply with DQO requirements detailed in NEPM, namely precision, accuracy, representativeness, completeness and comparability. | The assessment referred to in the comment was periously provided in Appendix F and Appendix G. QAQC tables were provided in Appendix G. |  |  |  | Open
70 |  |  |  | 9.0 CONCEPTUAL SITE MODEL POST-REMEDIATION | The pre remediation CSM must be updated and is expected to be provided in a tabulated format | Please refer to the amendments to Section 7 (former Section 9) |  |  |  | Open
71 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | 2. IMPORTANT INFORMATION ABOUT Coffey TETRA TECH COFFEY REPORT | Noting this section is currently blank | Please refer to the 'Statement of Limitations' included in the Site Auditor Package. |  |  |  | Open
72 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX A: FIGURES | General comment - consider rephrasing notes in figures relating to demolition. For example, Figure 2 states "the site is currently undergoing demolition and areas sealed with concrete is subject to change". Demolition has now been complete and Figures should be updated to avoid confusion | A note has been added to Figure 2 and Figure 3 to clarify the aerial photopgrah is of the Site pre-demolition and pre-remediation. |  |  |  | Open
73 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX A: FIGURES | Figure 2 - no legend descriptions for locations labelled red | Please refer to amendments to Figure 2 and Figure 3. Samples labelled red have been recoloured. |  |  |  | Open
74 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX A: FIGURES | Figure 3 looks similar to Figure 2 - should Figure 3 only capture locations where exceedances were identified? Suggest Coffey rename the figure "Exceedances of the Adopted Investigation Levels and Fill Depth" or similar | Tetra Tech Coffey preference is to not amend the figure as it shows fill depths in locations which may or not have an excedence, and is consistent with figures previous included in the RAP and Supplementary Investigation. The title of the Figure "Summary of Human Heath Exceedences and Fill Depth" is considered to be appropriate. |  |  |  | Open
75 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX A: FIGURES | Figure 4B: "materials to be recovered at the BMI Group Redbank Resource Recovery Facility" - for what purpose? Reuse by the landfill? If so, consider whether Figure 4 is actually required. If it is to be retained please confirm if excavation at Area 4A and 4B were actually required. It maybe useful to include a cross section (or incorporate with the graphical CSM) | Figure 4A and Figure 4B are required to address comment 36. Reference to the redbank resource recovery facility have been removed. Please refer to additional note included in the Figure. Please refer to graphical CSM included in Figure 15. |  |  |  | Open
76 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX A: FIGURES | Figure 7: Estimated dimensions of trenches required (length, width, depth) | Need to get information from EPS |  |  |  | Open
77 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | General Comment | Provide comment on topography change and stormwater drainage, if any, post remediation | Please refer to Section 6.6.2 |  |  |  | Open
78 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX C: DATA TABLES | Please include sample depth | Sample depth is included in Appendix C.1 and C.2. Logs of material samples are included in the Appendix B. |  |  |  | Open
79 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX C: DATA TABLES | A QA/QC of analytical data has not yet been completed. This is to be undertaken by the CLA in the future | QA/QC tables and an asessment of this data was provided in Appendix G. |  |  |  | Open
80 | LC (Epic) | Rev B, 22/04/2024 | 2024-02-29 | APPENDIX D: PHOTOGRAPHS | It would be beneficial to provide photos for general site condition pre and post remediation | Photographs have been included in Appendix D.3 and are referred to at the end of Section 6.2. |  |  |  | Open
Drop Down Menus
Document | Reviewers | Doc Rev | Site | Reference/ Report Section | [5 empty] | Status list
784-BNEEN282781 | LC (Epic) | Rev B, 22/04/2024 | 114 Newdegate Street, Greenslopes (Lot 123-125 RP46047) | [6 empty] | Closed
1.0 Introduction
|  |  |  | 2.0 Technical Framework | [5 empty] | Open
3.0 Structure of Validation Report
3.1 Site Characterisation
3.2 Remediation Plan
3.3 Remediation and Validation Works
3.4 Site Suitability Statement
4.0 Site Description
4.1 Site Identification
4.2 Site History
4.3 Environmental Management Register
4.4 Environmental Setting
4.5 Regional Ecosystems
4.6 Environmental Values and Water Quality Objectives
4.6.1 Environmental Values
4.6.2 Water Quality Objectives for Protection of Environmental Values
5.0 Summary of Contamination
5.1 Ground Conditions
5.2 Groundwater
6.0 Pre-Remediation Conceptual Site Model
6.1 Tabulated CSM
7.0 Remediation Plan
7.1 Remediation Strategy
7.2 Remediation Objective
7.3 Remediation Criteria
7.4 Materials Requiring Remediation
8.0 Remediation and Validation Works
8.1 Key Parties Involved in Remediation and Validation
8.2 Summary of Remedial Works
8.3 Inspections During Remediation
8.4 Air Quality Monitoring During Remediation
8.4.1 OCP Pesticides
8.4.2 Asbestos
8.5 Excavation of Materials Requiring Remediation
8.6 Excavation of Service Trenches
8.7 Disposal of Excavated Materials
8.8 Imported Materials
8.9 Validation Sampling
8.9.1 Overview
8.9.2 Final Validation Sample Results
8.9.3 Area used to Stockpile Imported Materials
8.9.4 Imported Materials
8.10 Quality Assurance and Quality Control
9.0 CONCEPTUAL SITE MODEL POST-REMEDIATION
10.0 CONCLUSIONS
11. SITE SUITABILITY STATEMENT
2. IMPORTANT INFORMATION ABOUT Coffey TETRA TECH COFFEY REPORT
APPENDIX A: FIGURES
APPENDIX B: SITE IDENTIFICATION INFORMATION
APPENDIX C: DATA TABLES
APPENDIX D: PHOTOGRAPHS
D.1 Boundary fence photographs
D.2 Validation Sample Photographs
APPENDIX E: LABORATORY REPORTS
APPENDIX F: QAQC REPORT
F.1 Field Quality Control (QAQC) Samples
F.2 Laboratory Quality Assurance Quality Control
F.3 Summary of Data Quality Review
F.4 QAQC rpd and blank sample Tables
APPENDIX G: DQO/DQIS
G.1 Data Quality Objectives
G.2 Data Quality Indicators
APPENDIX H: REMEDIATION CONTRACTOR INFORMATION
H.1 Waste Disposal Permits
H.2 Disposal Records
H.3 Imported Fill Records
APPENDIX I: AIR MONITORING
I.1 OCP Dust Monitoring Report
I.2 Asbestos Air Monitoring Reports
APPENDIX J: MODIFIED ARSENIC CRITERIA AND ASSESSMENT
APPENDIX K: SUPPORTING DOCUMENTS
K.1 Coffey 2013 Phase 1 Contaminated Land Assessment
K.2 Coffey 2013 Phase 2 Contaminated Land Assessment
K.3 Coffey 2019 Delineation of Organochlorine Soil Impacts
K.4 Tetra Tech Coffey 2021 Sampling, Analysis and Quality Plan
K.5 Tetra Tech Coffey 2022 Supplementary Investigation
K.6 Tetra Tech Coffey 2023 Remediation Action Plan
Other Supporting Information
General Comment
DRAFT